## Mantis_bug_Rootcause_SolvingProcess
Id	Reproducibility	Category	Root Cause	Solving Procedure
189	always	User Interface	Placed Wrong Text	Replace Correct Text
190	always	Functional	“Consolidated View Trip” is not added in Permission List.	Added “Consolidated View Trip” in Permission List.
119	always	User Interface
191	always	Functional	Have not put any checking whether a supervisor has already assigned to any plant or not while uploading CSV.	Added checking whether a a supervisor is already assigned to any plant or not while importing CSV.
192	always	Functional	Have not put the "Balance Initiation" coding while importing Plant CSV.	Implemented the "Balance Initiation" code while importing Plant CSV.
51	always	Functional	Text error in “Edit User” page. Validation error.	Added proper validation in “Edit User” page. Changed text as per requirement.
68	always	Functional	Missing proper validation while checking for duplicate Email Address while Editing User	Changed the validation code of duplicate Email Address while editing User.
32	always	Functional	No validation is added for creating duplicate State Name and State Code. Searching with respect to State Code is not added.	Added validation for checking duplicate State Name and State Code while creating State. Searching with respect to State Code added.
33	always	Functional	No validation is added for creating duplicate City Name and City Code. All the states (with respect to active/inactive) are shown in State drop down while adding City . No alphabatical order is added for State.	Added validation for checking duplicate City Name and City Code while creating City. Showing only ‘Active’ State in alphabatical order in dropdown while adding City.
34	always	Functional	No validation is added for creating duplicate Category Name	Added validation for checking duplicate Category Name while creating Category
35	always	Functional	No validation is added for creating duplicate Subcategory Name. All the categories (with respect to active/inactive) are shown in Category drop down while adding Subcategory. Import functionality is not working due uploading wrong formatted CSV.	Added validation for checking duplicate Subcategory Name while creating Subcategory. Showing only ‘Active’ Category in alphabatical order in dropdown while adding Subcategory. A proper formatted CSV is solving the import issue.
36	always	Functional	Import functionality is not working due uploading wrong formatted CSV.	A proper formatted CSV is solving the import issue.
37	always	Functional	No validation is added for creating duplicate Plant Name. Missing proper validation through out the module under the mentioned condition.	Added validation for checking duplicate Plant Name while creating Plant. Adding proper validation as per mentioned in the bug.
84	always	Functional	No message is given while ‘Inactive’ user tried to login and failed.	Added proper failure message while ‘Inactive’ user tried to login and failed.
101	always	Functional	CSV import issue occurs due to putting wrong table field name in code	Added the proper table field name in code.
31	always	Functional	Link is not working because local server link is given.	Added Client’s server link to resolve the issue
41	always	Functional	Validation error for duplicate State add	Solving Validation error with proper condition
44	always	Functional	Validation error and Javascript throught out the module.	Added proper Validation and Javascript Validation in the module
55	always	Functional	User role was not mandatory while adding User	Changed ‘User Role’ as mandatory while adding User.
63	always	Functional	Before implementing the total functionality of this page many testing data were added manually in database for viewing this page, all of them were correct then, that’s why the error was coming	Cleared the databse totally and inserted new correct data.
64	always	Functional	As all the modules are implemented in AngularJS and only ‘User’ module is implemented in PHP , thats why AngularJS’s ‘Logout’ function is not working in ‘User’ section.	Implented Laravel’s Logout functionality.
66	always	Functional	Missing proper validation sequence.	Added properly sequenced validation message.
69	always	Functional	Before implementing the total functionality of this page many testing data were added manually in database for viewing this page, all of them were correct then, that’s why the error was coming	Cleared the databse totally and inserted new correct data.
75	always	Functional	Missing proper validation for Contact Number and Email	Added proper validation for Contact Number and Email
76	always	Functional	Permission and Authentication related issue.	Solving the Permission and Authentication related issue.
77	always	Functional	Browser Cache problem	Cleared the Browser Cache
81	always	Functional	Wrong data coming for User role while editing User.	Getting proper data of User Role while editing User.
92	always	Functional	Proper Validation missing.	Added Proper validation.
97	always	Functional	Proper sorting functionality were missing.	Proper sorting functionality with pagination are added.
99	always	Functional	Proper searching functionality were missing.	Proper searching functionality with pagination are added.
100	always	Functional	Unable to replicate issue	Unable to replicate issue
105	always	User Interface	Same session name is used for logged in user’s phone number and edited user’s phone number.	Changed the Edited User’s session name for phone number
106	always	Functional	CHANGE REQUEST	Removed ‘Active’ checkbox and added ‘Next’,’Previous’ button for navigating to different tab
108	always	User Interface	No label were added where there is need to upload file in add/edit form.	Added proper label where it is needed to upload file.
109	always	Functional	Advance amount is shown instead of DSL amount	Showing proper DSL amount.
120	have not tried	Functional	CHANGE REQUEST and Date field validation were missing	User will be able to click on Next button if he filled out all the fields in current page, Change button color as per requirement. Validating date field as per requirement.
125	always	Functional	CHANGE REQUEST	we are taking the 'MINIMUM' year from the database and showing from that minimum year to current year in drop down.
128	always	Functional	CHANGE REQUEST	Removing ‘Active’ checkbox
147	always	Functional	Validation missing for ‘Years’ field if no single data found for the laser.	Proper validation added.
150	always	User Interface	Wrong text placed in the modules.	Proper text placed .
151	always	Functional	CHANGE REQUEST	Removing ‘Active’ checkbox while adding data, Showing ‘Active’ checkbox as it was there while editing data
152	always	Functional	Wrong sample file path given.	Added correct sample file path in different module.
156	always	User Interface	CHANGE REQUEST	Showing ‘Dates’ in Notification modules as per mentioned.
157	always	Functional	'Status’ field is present in every sample CSV file	Removed ‘Status’ field from every sample CSV file.
159	always	Functional	Spelling mistakes. Supervisor’s permission related issue in listing page.	Added correct spelling. Solving the permission related issue for Supervisor.
161	always	Functional	Supervisor’s permission related issue in listing page.	Solving the permission related issue for Supervisor.
162	always	Functional	One supervisor is assigned to many plants	Assign one supervisor to one plant only.
164	have not tried	Functional	Permission related issue.	Solving the permission related issue throughout the site.
167	always	Functional	Permission related issue.	Solving the permission related issue throughout the site.
168	always	Functional	Edit of trip could be done in case of Closed trip	Removing ‘Edit’ option for Closed Trip.
169	always	Functional	CHANGE REQUEST	Giving view permission to Supervisor for Plant, Party module
170	always	User Interface	CHANGE REQUEST	Showing Details page as per discussed. Added ‘N/A’ where there is no data.
172	always	Functional	Spelling Mistakes. Wrong data entry in database while adding payment to Plant	Solved the Spelling error. Changed the code for proper data entry in database.
173	always	User Interface	CHANGE REQUEST	Adding proper space as per mentioned.
175	always	Functional	Permission related issue.	We are giving 'view' permission of Country, State, City to the Supervisor.
177	always	Functional	Permission related issue.	Solving the permission related issue
179	always	User Interface	Permission related design issue.	Solving the permission related design issue
180	always	User Interface	Permission related issue.	Solving the permission related issue
185	always	Functional	Permission related issue.	Solving the permission related issue
186	always	Functional	Permission related issue.	Solving the permission related issue
40	always	Design	Design Issue.	A loader is added
52	N/A	Functional	Missing User Details and Status	Added User Details and Status
53	always	User Interface	Wrong text given	Text is changed
54	always	User Interface	Validation message missing	Added Validation Message
56	always	Functional	Validation has not been implented in Add/Edit User page	Validation is implemented in Add/Edit User page
59	always	User Interface	Validation message missing	Added Validation Message
67	always	User Interface	CHANGE REQUEST	Flash message implemented.
74	always	Functional	Validation message missing	Added Validation Message
98	always	User Interface	Design Issue.	Solved Design issue.
123	always	Design	Design Issue.	Solved Design issue.
124	always	User Interface	Title missing in different icon (Edit, Delete, View etc) in listing page	Added title in different icon in listing page
126	always	Design	'Action’ and ‘View’ icon were different in User Module from rest of the module.	Changing the ‘Action’ and ‘View’ icon in User Module as per other module.
158	always	User Interface	CHANGE REQUEST	added row to show total credit and debit amount
163	always	User Interface	input type ‘number’ is added for ‘Balance Amount’ field	Changed the ‘number’ type field to ‘text’ type field.
171	always	Functional	CHANGE REQUEST	Download link is added for every file mentioned.
48	always	Functional	Validation is missing	Added Validation
91	always	User Interface	Validation missing for ‘Import’ button	Validation added for ‘Import’ button.
107	always	User Interface	CHANGE REQUEST	Making present date selected for calendars.
110	always	User Interface	GPS trip status is present while adding/editing trip	Removing GPS trip status while adding/editing trip.
121	always	Design	Design Issue.	Solved Design issue.
122	always	Design	Design Issue.	Solved Design issue.
129	always	User Interface	CHANGE REQUEST	Changing date format as per requirement.
145	always	User Interface	Design Issue.	Solved Design issue.
148	always	User Interface	CHANGE REQUEST	Changing date format as per requirement.
154	always	User Interface	input type ‘number’ is added for ‘Amount’ field	Changed the ‘number’ type field to ‘text’ type field.