## Mantis_bug_Rootcause_SolvingProcess
Id	Reproducibility	Category	Root Cause 1	Solving Procedure 1	Root Cause 2	Solving Procedure 2	Root Cause 3	Solving Procedure 3
48	always	Functional	Validation is missing	Added Validation	Not redirecting the page to ‘User Role’ page.	Redirecting the page to ‘User Role’ page.
44	always	Functional	Validation error and Javascript throught out the module.	Added proper Validation and Javascript Validation in the module	Selecting All and De-Select All functionality is not implemented properly	Selecting All and De-Select All functionality is not plemented properly
64	always	Functional	As all the modules are implemented in AngularJS and only ‘User’ module is implemented in PHP , thats why AngularJS’s ‘Logout’ function is not working in ‘User’ section.	Implented Laravel’s Logout functionality.	Browser cache issue.	Cleared the browser cache.
35	always	Functional	No validation is added for creating duplicate Subcategory Name. All the categories (with respect to active/inactive) are shown in Category drop down while adding Subcategory. Import functionality is not working due uploading wrong formatted CSV.	Added validation for checking duplicate Subcategory Name while creating Subcategory. Showing only ‘Active’ Category in alphabatical order in dropdown while adding Subcategory. A proper formatted CSV is solving the import issue.	Browser cache issue.	Cleared the browser cache.
52	N/A	Functional	Missing User Details and Status	Added User Details and Status	Status missing	Added Status
31	always	Functional	The site name is given as ‘sslogistic’ instead of ‘sslogistics’	Changed the site name to ‘sslogistics’	Link is not working because local server link is given.	Added Client’s server link to resolve the issue
100	always	Functional	Unable to replicate issue	Unable to replicate issue	File was not uploaded properly to the server.	File uploaded properly to the server.
97	always	Functional	Proper searching functionality were missing.	Proper searching functionality with pagination are added.	Proper sorting functionality were missing.	Proper sorting functionality with pagination are added.
154	always	User Interface	input type ‘number’ is added for ‘Amount’ field	Changed the ‘number’ type field to ‘text’ type field.	input type ‘number’ is added for ‘Amount’ field in ‘Petrol Pump Payment’ module.	Changed the ‘number’ type field to ‘text’ type field.
107	always	User Interface	CHANGE REQUEST	Making present date selected for calendars.	Showing present date as default date in textbox	Removing present date from date textbox, instead only selecting the present date in calendar	Start date and End Date comparison validation were missing.	Added Start date and End Date comparison validation
159	always	Functional	Spelling mistakes. Supervisor’s permission related issue in listing page.	Added correct spelling. Solving the permission related issue for Supervisor.	Replaced the Admin’s action too with status	Revert back the functionalities of Admin as per there previously
223	always	Functional	Previously displayed message was not removed	Deleting previously displayed message once it is hidden.

124	always	User Interface	Title missing in different icon (Edit, Delete, View etc) in listing page	Added title in different icon in listing page
126	always	Design	'Action’ and ‘View’ icon were different in User Module from rest of the module.	Changing the ‘Action’ and ‘View’ icon in User Module as per other module.
158	always	User Interface	CHANGE REQUEST	added row to show total credit and debit amount
163	always	User Interface	input type ‘number’ is added for ‘Balance Amount’ field	Changed the ‘number’ type field to ‘text’ type field.
171	always	Functional	CHANGE REQUEST	Download link is added for every file mentioned.
48	always	Functional	Validation is missing	Added Validation
91	always	User Interface	Validation missing for ‘Import’ button	Validation added for ‘Import’ button.
107	always	User Interface	CHANGE REQUEST	Making present date selected for calendars.
110	always	User Interface	GPS trip status is present while adding/editing trip	Removing GPS trip status while adding/editing trip.
121	always	Design	Design Issue.	Solved Design issue.
122	always	Design	Design Issue.	Solved Design issue.
129	always	User Interface	CHANGE REQUEST	Changing date format as per requirement.
145	always	User Interface	Design Issue.	Solved Design issue.
148	always	User Interface	CHANGE REQUEST	Changing date format as per requirement.
154	always	User Interface	input type ‘number’ is added for ‘Amount’ field	Changed the ‘number’ type field to ‘text’ type field.